# Timeline planning

Semester 1 – FYP1 (Weeks 1–14)

| Weeks | Task | Duration | Description / Methodology | Notes / Overlap |
| --- | --- | --- | --- | --- |
| 1 | Project kickoff & scope finalization | 3 days | Define project objectives, scope, deliverables, and success criteria. Meet supervisor to align expectations. | Start of project |
| 1–2 | Literature review – ZKP authentication | 10 days | Study existing research on zero-knowledge proof protocols for authentication. Identify gaps and relevant methods. | Can overlap with project planning |
| 2–3 | Literature review – AI anomaly detection | 10 days | Review Isolation Forest, Autoencoder, and other anomaly detection methods. Summarize findings and relevance. | Can overlap with ZKP review end |
| 3–4 | System architecture design | 7 days | Design overall system, including backend, frontend, AI module, ZKP flow, and database schema. | Overlaps with last week of literature review |
| 4–5 | Proposal drafting | 7 days | Write proposal including objectives, methodology, expected outcomes, and preliminary system design. | Overlaps with architecture design |
| 5 | Proposal revision & feedback | 3 days | Incorporate supervisor feedback. Refine methodology, scope, and diagrams. | Parallel with small backend experiment |
| 6 | Proposal defense prep | 2–3 days | Prepare slides and rehearse defense; focus on objectives, methodology, and expected contributions. |  |
| 7 | Proposal defense | 1 day | Formal presentation to supervisor / panel. |  |
| 7–9 | Backend prototype planning & coding | 10 days | Build minimal backend to handle authentication, basic data storage, and APIs. Follow Agile mini-sprints. | Can overlap with frontend skeleton development |
| 9–10 | Frontend prototype development | 7 days | Create a basic UI for registration, login, and user interface navigation using Flutter. | Overlaps with backend testing |
| 10–11 | Backend + frontend integration | 7 days | Connect backend APIs with frontend UI, implement basic ZKP flow. |  |
| 11–12 | Half-working prototype testing & feedback | 7 days | Conduct unit and integration testing; gather supervisor feedback to refine system. | Overlaps with some report drafting |
| 12–14 | FYP1 documentation | 10 days | Document literature review, methodology, architecture, prototype design, and preliminary results. | Can overlap with final prototype testing |

Semester 2 – FYP2 (Weeks 1–14)

| Weeks | Task | Duration | Description / Methodology | Notes / Overlap |
| --- | --- | --- | --- | --- |
| 1–2 | Full backend development | 10 days | Implement full backend, including ZKP authentication, data management, and APIs. Use Agile sprints for iterative development. | Can start frontend skeleton at same time |
| 2–3 | Backend optimization & bug fixing | 7 days | Refactor code, improve performance, handle errors, and optimize API response times. | Overlaps with AI model setup |
| 3–4 | Frontend integration & polishing | 7 days | Enhance UI/UX, connect additional backend endpoints, and ensure smooth user experience. | Overlaps with backend testing |
| 4–5 | AI model development | 10 days | Train AI models (Isolation Forest + Autoencoder) for anomaly detection using preprocessed dataset. | Overlaps with frontend polishing |
| 5–6 | AI model testing & tuning | 7 days | Evaluate model performance, tune hyperparameters, and select the best-performing model. | Can start integration in parallel |
| 6–7 | AI integration into mobile app | 7 days | Convert AI model to mobile-friendly format (e.g., TensorFlow Lite) and integrate into Flutter app. | Overlaps with internal system testing prep |
| 7–8 | Internal system testing | 7 days | Conduct thorough functional, unit, and integration testing across backend, frontend, and AI modules. | Overlaps with final AI tuning |
| 8–9 | Integration testing | 7 days | End-to-end testing of the full system workflow with real-like data. | Overlaps with small bug fixes in backend/frontend |
| 9–10 | Security & penetration testing | 7 days | Test authentication, replay attacks, session hijacking, and ZKP security. Document vulnerabilities. | Overlaps with UI/UX tweaks |
| 10–11 | User acceptance testing (SMEs) | 7 days | Collect feedback from subject matter experts, measure usability, and verify system meets project goals. | Can overlap with final performance tuning |
| 11–12 | Final improvements & bug fixes | 7 days | Address UAT feedback, optimize performance, and ensure system stability. | Parallel with report documentation |
| 12–13 | Final report & documentation | 10 days | Write detailed chapters: methodology, implementation, results, discussion, and conclusion. Include diagrams and screenshots. | Overlaps with final improvements |
| 13–14 | Final deployment & submission | 5 days | Deploy fully functional system, prepare presentation slides, submit project deliverables. | Mostly independent |

Option 3: The "Modern & Integrated" Timeline

This is the most visually appealing and modern approach, often created with specialized tools or more advanced graphic design. It integrates both semesters into one fluid view.

Visual Style: A central timeline with grouped "swimlanes" for different types of work (e.g., Research, Build, Test). Icons and milestone markers are used heavily.

Conceptual Layout:

text

TIMELINE (Weeks) > 1---2---3---4---...---7---...---14---1---2---...---14

FYP 1                            |    FYP 2

----------------------------------------------------------------------

[PLAN & DESIGN]

• Lit Review ▢▢▢▢▢▢▢▢

• Arch Design   ▢▢▢▢▢▢▢

• Proposal        ▢▢▢▢▢▢▢◈ (Defense)

----------------------------------------------------------------------

[PROTOTYPE / BUILD]

• Backend           ▢▢▢▢▢▢▢▢▢▢

• Frontend               ▢▢▢▢▢▢▢

• AI Model                                ▢▢▢▢▢▢▢▢▢▢

----------------------------------------------------------------------

[TEST & REFINE]

• Integration          ▢▢▢▢▢▢▢

• System Test                    ▢▢▢▢▢▢▢▢▢▢▢▢

• UAT                                            ▢▢▢▢▢▢▢

----------------------------------------------------------------------

[DOCUMENTATION]

• FYP1 Doc                 ▢▢▢▢▢▢▢▢▢▢

• Final Report                                        ▢▢▢▢▢▢▢▢▢▢★(Submit)

(▢ = Task duration, ◈ = Milestone, ★ = Final Deliverable)

Actionable Recommendations & Tools:

- For Quickest Result (Option 1): Use PowerPoint's built-in SmartArt or Chart tools. It integrates seamlessly with your proposal deck.

- For Most Detailed & Accurate (Option 2): Use Microsoft Excel or Google Sheets. It gives you the most control over dates and dependencies.

- For Most Professional Look (Option 3): Use a free trial of a dedicated tool like:

  - Gantt.io (integrates with Google Sheets)

  - TeamGantt

  - Instagantt
These tools are built specifically for this and make creating polished, interactive charts very easy.

TIMELINE (Weeks) > 1---2---3---4---5---6---7---...---14---1---2---3---4---5---6---7---...---14

FYP 1: PROPOSAL & PROTOTYPING          |    FYP 2: FULL DEVELOPMENT & SUBMISSION

------------------------------------------------------------------------------------------

[PLAN & DESIGN].......#1A6FA5

• Lit Review     ▢▢▢▢▢▢▢

• System Design      ▢▢▢▢▢

• Proposal & Def      ▢▢▢▢▢▢◈ (Proposal Defense)

------------------------------------------------------------------------------------------

[PROTOTYPE / BUILD]...#56A36C

• Backend (P1)                ▢▢▢▢

• Frontend (P1)                   ▢▢▢

• Full Backend (P2)                        ▢▢▢▢

• AI Model (P2)                                ▢▢▢▢▢▢

• Frontend+AI (P2)                              ▢▢▢▢▢

------------------------------------------------------------------------------------------

[TEST & REFINE].......#E67E22

• Integrate & Test (P1)             ▢▢▢▢

• System Testing (P2)                          ▢▢▢▢▢▢

• Security Testing                             ▢▢▢▢▢▢

• UAT (P2)                                                ▢▢▢

• Final Polish                                               ▢▢▢

------------------------------------------------------------------------------------------

[DOCUMENTATION].......#95A5A6

• FYP1 Doc                          ▢▢▢▢▢▢

• Final Report (P2)                                        ▢▢▢▢▢▢▢▢★(Final Submission)

# After madam comment one

| Phase | Description | Tasks from Your Timeline |
| --- | --- | --- |
| 1. Requirements Planning / Quick Analysis | Rapid gathering of requirements, defining objectives, scope, and constraints. Focus on essential functionality. | - Project kickoff & scope finalization- Initial literature review (ZKP & AI)- Early architecture planning |
| 2. User Design / Prototyping | Build iterative prototypes (backend, frontend, AI modules) for early feedback. | - Initial prototype (backend + frontend skeleton)- UI mockups- Early AI module prototype |
| 3. Construction / Iterative Development | Parallel development of modules with short sprints, frequent iterations, and continuous integration. | - Backend full development- Frontend integration- AI model development & integration- Refinement after testing |
| 4. Cutover / Testing & Implementation | Final system testing, performance tuning, security checks, user acceptance testing, and deployment. | - Internal system testing- Integration testing- Security & penetration testing- UAT- Final deployment |
| 5. Documentation / Feedback Loop | Documentation evolves along with each prototype iteration; continuous improvements based on feedback. | - FYP1 documentation- Final report- Diagrams/screenshots updates during iterations |

FYP RAD Gantt Timeline (28 Weeks)

| Week | Dates | Phase | Key Tasks |
| --- | --- | --- | --- |
| 1 | 8–14 Oct | RP | Project kickoff, define objectives, scope, success criteria |
| 2 | 15–21 Oct | RP | Literature review – ZKP & AI, identify gaps |
| 3 | 22–28 Oct | UD | Initial prototype planning, backend + frontend skeleton |
| 4 | 29 Oct–4 Nov | UD | Build minimal backend & frontend prototype (half-development) |
| 5 | 5–11 Nov | UD | Continue prototype, basic AI module experiment |
| 6 | 12–18 Nov | UD | Prototype testing, gather supervisor feedback |
| 7 | 19–25 Nov | UD | Refine prototype based on feedback |
| 8 | 26 Nov–2 Dec | RP/UD | Proposal drafting (incorporate prototype insights) |
| 9 | 3–9 Dec | RP/UD | Proposal revision & supervisor feedback |
| 10 | 10–16 Dec | DOC | FYP1 documentation start (literature review, methodology, prototype design) |
| 11 | 17–23 Dec | DOC | Continue FYP1 documentation |
| 12 | 24–30 Dec | DOC | Continue FYP1 documentation |
| 13 | 31 Dec–6 Jan | UD | Final prototype iteration (half-developed) |
| 14 | 7–13 Jan | RP/UD/DOC | Proposal presentation / defense; finalize FYP1 doc |

⚠ February holiday: 28 Jan – 27 Feb – No work scheduled

| Week | Dates | Phase | Key Tasks |
| --- | --- | --- | --- |
| 15 | 28 Feb–6 Mar | CD | Resume full development: backend + frontend + AI module |
| 16 | 7–13 Mar | CD | Continue full development (iterative sprints) |
| 17 | 14–20 Mar | CD | Integrate backend, frontend, and AI |
| 18 | 21–27 Mar | CD | Internal testing & prototype refinement |
| 19 | 28 Mar–3 Apr | CT | Security & performance testing |
| 20 | 4–10 Apr | CT | User Acceptance Testing (SMEs) |
| 21 | 11–17 Apr | CD/CT | Bug fixing, final polishing |
| 22 | 18–24 Apr | DOC | Start FYP2 documentation, methodology, implementation |
| 23 | 25–30 Apr | DOC | Continue report writing, include screenshots & diagrams |
| 24 | 1–7 May | CT | Final system deployment & testing |
| 25 | 8–14 May | CT | Final system polish & performance optimization |
| 26 | 15–21 May | DOC | Final report completion |
| 27 | 22–27 May | DOC | Proofreading, formatting, finalize submission |
| 28 | 28 May | CT/DOC | Final presentation / project submission |

Phase Mapping (RAD-style)

| Phase | FYP1 Weeks | FYP2 Weeks |
| --- | --- | --- |
| Requirements Planning (RP) | 1–2, 8 | 15 |
| User Design / Prototyping (UD) | 3–7, 13–14 | 15–17 |
| Construction / Iterative Development (CD) | 4–7, 13 | 15–21 |
| Cutover / Testing & Implementation (CT) | 6, 18–21, 24–25, 28 |  |
| Documentation / Feedback (DOC) | 10–14 | 22–27 |